Praxis Framework Professional

Competence Framework

Overview

Praxis contains three groups of competencies. Delivery competencies are based on the delivery section of the knowledge section, process competencies are based on individual processes defined in the method and interpersonal competencies address the corresponding section of the knowledge section.

There is only one competency for each function or process and in practice each of these will need to be adapted to suit the setting in which it is to be applied. That means that a competency must be aligned with the complexity of the work, the environment of the work and whether it is to be managed as a project, programme or portfolio.

The knowledge and method sections provide the overall structure of the competency framework and more detailed information for the knowledge and performance criteria. In return the performance criteria defined in the competencies provide benchmarks of individual performance.

Competence

Method

Knowledge

Maturity

Organisational context

Benchmark criteria

Benchmark criteria

Goals and procedures

Goals and activities

Individual performance

Competencies are divided into three sections:

- Objectives (Purpose)

This section lists the specific goals that the competency is designed to achieve.

- Performance criteria (Professional Practice)

These are the criteria that someone must effectively perform to be deemed competent in achieving the goals.

- Knowledge and understanding (Technical Knowledge)

In order to effectively exhibit the performance criteria someone must have knowledge and understanding of the relevant principles, procedures, tools and techniques.

All of the 39 competencies are outlined in the following section. Those competencies that are not assessed as part of the Praxis Framework Professional have been greyed out, highlighting the 13 competencies that are assessed as part of the Praxis Framework Professional, which are identified with (M) signifying that they are ‘Mandatory’.

| Integrative Management Functions |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 1. Provide Assurance | The purpose of this competency is to achieve the goals of assurance, i.e. to: - review management planning - monitor effectiveness of functions and processes - give stakeholders confidence that the work is being managed effectively and efficiently |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on assurance K2. analyse how assurance procedures and techniques add value to the P3 functions and processes K3. evaluate different formats of assurance documentation K4. critically evaluate the need to adapt assurance throughout the project life cycle K5. evaluate methods of communicating assurance outcomes to stakeholders | Candidate can: P1. plan and initiate assurance P2. review the design and implementation of life cycle based processes P3. review the design and implementation of management plans P4. audit the performance of quality control activities and review any resulting corrective action P5. maintain assurance documentation P6. communicate the outcomes of assurance to stakeholders |

| Integrative Management Functions |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 2. Manage the Organisation (M) | The purpose of this competency is to achieve the goals of organisation management, i.e. to: - design an organisation appropriate to the scope of the work to be managed - identify and appoint members of the management team - maintain and adapt the organisation throughout the life cycle |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on organisation design K2. analyse methods to define roles and assess the suitability of potential team members K3. critically evaluate the skills required to lead and support an effective management team K4. evaluate methods to respond to changing organisational requirements during the life cycle K5. evaluate how assurance applies to the organisation K6. analyse the principles of staff redeployment | Candidate can: P1. design an appropriate organisation in accordance with the context of the work P2. recruit competent staff P3. lead, motivate, communicate and resolve conflict P4. maintain the organisation throughout the life cycle P5. demobilise the organisation P6. assure the maintenance of the organisation |

| Integrative Management Functions |  |  |  |
| --- | --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |  |
| 3. Manage Stakeholders (M) | The purpose of this competency is to achieve the goals of stakeholder management, i.e. to: - ensure that the views and attitudes of all stakeholders are understood; - influence stakeholders to be supportive of the work wherever possible; - maximise the impact of supportive stakeholders; - minimise the impact of unsupportive stakeholders. |  |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on managing stakeholders K2. analyse a procedure for stakeholder management K3. evaluate different formats of stakeholder management documentation K4. critically analyse methods for identifying stakeholders and appropriate sources of information K5. critically analyse techniques for assessing and documenting stakeholder interest and influence K6. evaluate communication channels and how to use them K7. evaluate methods of influencing stakeholders and negotiating with them K8. analyse how stakeholders and their interest and influence may change during the life cycle K9. evaluate how assurance applies to stakeholder management |  | Candidate can: P1. plan and initiate stakeholder management P2. identify stakeholders P3. assess stakeholders’ interests and influence P4. influence and communicate with stakeholders P5. maintain stakeholder management documentation P6. adapt communications throughout the life cycle P7. monitor and control stakeholder management P8. assure the quality of stakeholder management |

| Integrative Management Functions |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 4. Manage the Business Case | The purpose of this competency is to achieve the goals of business case management, i.e. to: - summarise context and delivery in a single document - explain the desirability, achievability and viability of the proposed work - develop the primary document that will be used to support a ‘go/no go’ decision at all gates in the life cycle - update and maintain the business case throughout the life cycle. |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on managing the business case K2. analyse the procedure for developing a business case K3. evaluate different formats of business case document K4. evaluate methods of summarising stakeholder requirements to represent desirability K5. evaluate methods of summarising detailed delivery documents covering scope, schedule, finance, risk, resource and change to represent achievability K6. evaluate methods of summarising detailed investment appraisal information to represent viability K7. critically evaluate methods of presenting the business case to relevant stakeholders to support decision making K8. critically analyse how the integrity of a business case is affected by progress and external factors K9. evaluate how assurance applies to the business case | Candidate can: P1. perform high level planning (to develop an outline business case) P2. summarise the output of detailed delivery documents (to develop a detailed business case) P3. use appropriate techniques to justify the project or programme P4. prepare and present the business case in a way that is likely to gain the support of stakeholders P5. develop arguments that justify the project or programme to stakeholders P6. respond to requests for additional information in a clear and timely way P7. monitor factors that influence the viability of the business case P8. assure the quality of the business case |

| Integrative Management Functions |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 5. Plan Governance | The purpose of this competency is to achieve the goals of governance planning, i.e. to: - describe the principles that should be used to manage the work - provide consistency with flexibility across multiple projects and programmes |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on management plans K2. evaluate different formats of a typical management plan K3. analyse how standard management plans may be tailored and/or adjusted during the P3 life cycle K4. evaluate how assurance applies to management plans | Candidate can: P1. identify external policy documents that will form part of the governance documentation P2. produce management plans to suit the context of the work P3. develop new management plans where organisational standards are not available P4. maintain management plans throughout the life cycle P5. assure the quality of management plans |

| Integrative Management Functions |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 6. Plan Delivery (M) | The purpose of this competency is to achieve the goals of delivery planning, i.e. to: - describe the objectives of the project, programme or portfolio - define the work required to achieve the objectives and describe how it will be performed - estimate the resources and finance needed to perform the work - document the plans and update them throughout the life cycle |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on delivery planning K2. analyse the way in which delivery plans should be prepared and presented K3. critically evaluate the estimating techniques applicable to different components of delivery K4. critically evaluate the modelling techniques applicable to schedules, finances, resources, risk and change K5. analyse how delivery plans are connected and how updates on plans impact on other plans K6. evaluate how assurance applies to delivery planning. | Candidate can: P1. prepare specifications that describe the scope of the work P2. prepare delivery plans for all aspects of the work, including schedule, finance, resources, risk, change P3. update plans throughout the life cycle P4. assure the quality of delivery planning |

| Integrative Management Functions |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 7. Exercise Control (M) | The purpose of this competency is to achieve the goals of control, i.e. to: - review performance against baselines - evaluate the effect of actual performance on future plans - take action as required to achieve planning targets or agree revised targets |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on control K2. evaluate a range of techniques for monitoring and reporting progress K3. evaluate methods of predicting future performance based on actual progress K4. critically evaluate the application and importance of tolerances K5. evaluate different formats of control documentation K6. evaluate how assurance applies to control | Candidate can: P1. plan and initiate control P2. co-ordinate the activity of the delivery team(s) P3. monitor progress P4. evaluate the impact of actual progress on the objectives P5. resolve issues and re-plan accordingly P6. maintain control documentation P7. assure the quality of the control procedure |

| Integrative Management Functions |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 8. Manage Information | The purpose of this competency is to achieve the goals of information management, i.e. to: - capture data accurately and consistently - develop usable information from raw data - maintain information securely and accessibly during its useful life - support effective decision making and communication |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on managing information K2. analyse a procedure for information management K3. evaluate methods for data capture and analysis K4. critically evaluate techniques for presenting information, and how to tailor information to meet different needs K5. evaluate information storage and access methods including version control K6. evaluate how and when to archive or destroy information K7. evaluate how assurance applies to information management | Candidate can: P1. plan and initiate information management P2. collect data from a variety of sources P3. transform data into information P4. store, access and disseminate information P5. archive and destroy information as required P6. assure the quality of information management |

| Manage Scope |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 9. Manage Scope | The purpose of this competency is to achieve the goals of scope management, i.e. to: - identify stakeholder wants and needs - specify outputs, outcomes and benefits that meet agreed requirements - maintain scope throughout the life cycle |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on managing scope K2. analyse an overall procedure for managing scope K3. evaluate different formats of scope documentation K4. critically evaluate techniques to define and manage the scope of a project K5. analyse how requirements management, solution development, benefits management, change control and configuration management, work in unison to identify, define and control the scope of a project K6. evaluate how assurance applies to scope management | Candidate can: P1. plan and initiate scope management P2. work with stakeholders to determine and agree scope P3. accurately document, baseline and communicate scope P4. monitor work and ensure it accords to agreed scope P5. control changes and maintain scope documentation P6. assure the quality of scope management |

| Manage Scope |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 10. Manage Requirements | The purpose of this competency is to achieve the goals of requirements management, i.e. to: - ensure that all relevant stakeholders have the opportunity to express their wants and needs - reconcile multiple stakeholder requirements to create a single viable set of objectives - achieve stakeholder consensus on a baseline set of requirements |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on managing requirements K2. analyse a procedure for managing requirements K3. evaluate different formats of requirements management documentation K4. critically evaluate methods of working with stakeholders to gather requirements and the sources of information that will support requirements management K5. evaluate methods of assessing stakeholders’ wants and needs, and managing stakeholders’ expectations K6. evaluate methods of prioritising and agreeing requirements with stakeholders K7. analyse the relationship between requirements, objectives and acceptance criteria K8. evaluate how assurance applies to requirements management | Candidate can: P1. plan and initiate requirements management P2. capture requirements from stakeholders P3. review the requirements to distinguish wants from needs P4. assess the requirements to look for overlaps, gaps and conflicts P5. evaluate requirements and select those that can most effectively satisfy the majority of stakeholder requirements P6. develop a set of objectives that reflect stakeholders' requirements P7. baseline the requirements P8. assure the quality of requirements management |

| Manage Scope |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 11. Develop Solution | The purpose of this competency is to achieve the goals of solutions development, i.e. to: - evaluate baseline requirements and alternative solutions to achieve them - select the optimum solution - create a specification for the solution |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on developing a solution K2. evaluate the relationship between solutions and requirements K3. analyse a procedure for developing solutions K4. evaluate different formats of solutions development documentation K5. evaluate the sources of information and expertise for the development of solutions and how to analyse such information (including using lessons learned) K6. evaluate methods of working with stakeholders to develop solutions and manage stakeholder expectations K7. evaluate the reasons for developing a range of solutions and how these should be presented K8. evaluate how assurance applies to solutions development | Candidate can: P1. mobilise the necessary expertise to support the development of solutions P2. involve stakeholders in the evaluation of potential solutions P3. agree the optimum solution with stakeholders P4. clearly document the agreed solution in a specification P5. assure the quality of solutions development |

| Manage Scope |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 12. Manage Benefits | The purpose of this competency is to achieve the goals of benefits management, i.e. to: - define benefits and dis-benefits of the proposed work - establish measurement mechanisms - implement any change needed in order to realise benefits - measure improvement and compare to the business case |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on managing benefits K2. analyse a procedure for managing benefits K3. evaluate different formats of benefits management documentation K4. critically evaluate mechanisms for quantifying and valuing benefits and dis-benefits K5. evaluate tools and techniques to measure benefits K6. critically evaluate the impact of change on stakeholders K7. evaluate different approaches to managing change K8. analyse the relationships between outputs, outcomes and benefits K9. evaluate how assurance applies to benefits management | Candidate can: P1. plan and initiate benefits management P2. define, document and communicate benefits and dis-benefits P3. define measurement mechanisms and implement throughout the life cycle P4. initiate and manage change P5. review achievement of benefits in the business case P6. assure the quality of benefits management |

| Manage Scope |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 13. Control Scope Change (M) | The purpose of this competency is to achieve the goals of change control, i.e. to: - capture stakeholders’ requests to make changes to scope - ensure that requests are only approved if viable and achievable - integrate changes into the existing scope. |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on controlling scope change K2. analyse a procedure for change control K3. evaluate different formats of change control documentation K4. analyse the reasons for scope change, the types of change requests that may emerge and how these can be managed K5. evaluate the need to record project changes and the impact of such changes on delivery plans K6. evaluate the importance of communicating decisions to stakeholders K7. evaluate how assurance applies to change control | Candidate can: P1. plan and initiate change control P2. capture and assess change requests P3. decide whether to accept change requests P4. implement accepted change requests P5. keep stakeholders informed P6. take action to manage any issues that arise P7. assure the quality of change control |

| Manage Scope |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 14. Manage the Configuration | The purpose of this competency is to achieve the goals of configuration management, i.e. to: - identify the products that will be treated as configuration items - support the assessment of change requests and document the results of change control - maintain the validity of the configuration and the accuracy of the configuration management system |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on configuration management K2. analyse a procedure for configuration management K3. evaluate different formats of configuration management documentation K4. evaluate how the configuration management system supports change control K5. evaluate methods of configuration status accounting, verification and audit K7. evaluate how assurance applies to configuration management | Candidate can: P1. plan and initiate configuration management P2. identify configuration items P3. use configuration records to support all aspects of scope management P4. maintain configuration management documentation P5. assure the quality of configuration management |

| Manage the Schedule |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 15. Manage the Schedule (M) | The purpose of this competency is to achieve the goals of schedule management, i.e. to: - determine timescales for the work - calculate profiles of resource demand - present schedule reports suitable for different stakeholders |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on managing the schedule K2. analyse a procedure for schedule management K3. evaluate different formats of schedule documentation K4. critically evaluate techniques for identifying work components K5. critically evaluate methods for modelling the performance of work K6. critically evaluate time and resource estimating techniques K7. analysis techniques and reporting formats K8. evaluate the importance of maintaining and updating the schedule K9. evaluate how assurance applies to schedule management | Candidate can: P1. plan and initiate schedule management P2. identify the work that must be performed to achieve objectives P3. model the way work will be performed P4. determine and apply suitable estimating methods for time and resource P5. schedule the work P6. agree schedules with stakeholders P7. determine and apply suitable reporting methods P8. assure the quality of schedule management |

| Manage Finance |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 16. Manage Finance | The purpose of this competency is to achieve the goals of financial management, i.e. to: - estimate the cost of achieving the objectives - assess the viability of achieving the objectives - secure funds and manage their release throughout the life cycle - set up and run financial systems - monitor and control expenditure |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on financial management K2. analyse a procedure for managing finance K3. evaluate different formats of financial management documentation K4. evaluate the relationship between investment appraisal, funding and budgeting and cost control K5. evaluate how assurance applies to financial management | Candidate can: P1. plan and initiate financial management P2. ensure the cost of the work is understood P3. identify the best means of funding the work P4. apply principles of financial and management accounting P5. maintain financial documentation P6. assure the quality of financial management |

| Manage Finance |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 17. Develop Investment Appraisal | The purpose of this competency is to achieve the goals of investment appraisal, i.e. to: - assess the viability of achieving the objectives - support the production of a business case |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on the investment appraisal K2. critically evaluate objective appraisal techniques and subjective appraisal techniques K3. evaluate the importance of maintaining and updating the appraisal K4. evaluate methods for presenting investment appraisal information K5. evaluate how assurance applies to investment appraisal | Candidate can: P1. determine factors affecting the appraisal P2. identify suitable appraisal techniques P3. perform an investment appraisal P4. present investment appraisal information as part of a business case P5. maintain investment appraisal documentation P6. assure the quality of investment appraisal |

| Manage Finance |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 18. Manage Funding | The purpose of this competency is to achieve the goals of funding, i.e. to: - determine the best way to fund the work - secure commitment from the fund holders - manage the release of funds throughout the life cycle |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on funding K2. analyse a procedure for funding K3. evaluate the benefits and drawbacks of different sources of funding K4. evaluate methods of synchronising funding and expenditure K5. evaluate different formats of funding documentation K6. evaluate how assurance applies to funding | Candidate can: P1. identify suitable sources of project or programme funds P2. compare different sources of funds and select the optimum combination P3. negotiate the terms and conditions for the provision of funds P4. co-ordinate drawdown of funds with expenditure P5. maintain funding documentation P6. assure the quality of the funding procedure |

| Manage Finance |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 19. Develop Budgets and Control Costs (M) | The purpose of this competency is to achieve the goals of budgeting and cost control, i.e. to: - determine the income and expenditure profiles for the work - develop budgets and align with funding - implement systems to manage income and expenditure |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on budgets and cost control systems K2. analyse a procedure for developing budgets and controlling costs K3. critically evaluate techniques for estimating and operating contingency and management reserves K4. evaluate cost attributes and payment types K5. evaluate different formats of budgetary and cost control documentation K6. evaluate how assurance applies to budgeting and cost control | Candidate can: P1. refine cost estimates and allocate costs to budgets P2. calculate values for contingency and management reserves P3. set up and manage cost control systems P4. co-ordinate expenditure with the availability of funds P5. maintain budget and cost control documentation P6. assure the quality of budgets and cost control |

| Manage Risk |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 20. Manage Risk (M) | The purpose of this competency is to achieve the goals of risk management, i.e. to: - ensure that levels of overall risk within a project, programme or portfolio are compatible with organisational objectives - ensure that individual risks and responses are identified - minimise the impact of threats to objectives - optimise opportunities within the scope of work |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on risk management K2. analyse a procedure for risk management K3. evaluate different formats of risk management documentation K4. critically evaluate methods for identifying risk and appropriate sources of information K5. critically evaluate techniques for assessing threats and opportunities K6. critically evaluate types, and appropriate use, of risk response actions K7. evaluate risk attitude and risk appetite K8. evaluate how risk events and overall risk may change during the life cycle K9. evaluate how assurance applies to risk management | Candidate can: P1. plan and initiate risk management P2. identify risk events P3. assess the probability and impact of risk events P4. plan responses to risk events P5. implement responses to risk events and maintain acceptable levels of overall risk P6. maintain risk management documentation P7. monitor and control risk management P8. assure the quality of risk management |

| Manage Change |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 21. Manage Change | The purpose of this competency is to achieve the goals of change management, i.e. to: - define the organisational change required to convert outputs into benefits; - ensure the organisation is prepared to implement change; - implement the change and embed it into organisational practice. |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on change management K2. analyse a procedure for change management K3. evaluate different formats of change management documentation K4. analyse the use of change management models K5. evaluate methods of communicating change K6. evaluate techniques for, and importance of, assessing readiness to change K7. analyse methods for overcoming resistance to change K8. evaluate methods for, and importance of, ensuring change is embedded in business as usual K9. evaluate how assurance applies to change management | Candidate can: P1. plan and initiate change P2. identify the change required to existing practices P3. assess the organisation’s readiness to change P4. communicate and implement change P5. ensure that new practices are embedded in business as usual P6. maintain change management documentation P7. assure the quality of change management |

| Manage Resources |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 22. Manage Resources | The purpose of this competency is to achieve the goals of resource management, i.e. to: - determine the best way to resource the work - acquire and mobilise the necessary resources - manage resources throughout the life cycle - demobilise resources at the end of the life cycle - finalise all contractual arrangements |  |
|  | Candidate can: K1. the context of the work and its impact on resource management K2. analyse a procedure for managing resources K3. evaluate different formats of resource management documentation K4. evaluate the relationship between procurement, contract management and mobilisation K6. evaluate how assurance applies to resource management | Candidate can: P1. plan and initiate resource management P2. identify the best resourcing method for delivering the scope of work P3. negotiate the provision of internal resources P4. select and appoint external suppliers P5. mobilise resources throughout the life cycle P6. administer and control resources P7. maintain resource management documentation P8. assure the quality of resource management |

| Manage Resources |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 23. Procure Resources | The purpose of this competency is to achieve the goals of procurement, i.e. to: - identify potential external suppliers - select external suppliers - acquire commitment to provision of internal resources |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on procurement K2. analyse a procedure for procurement K3. evaluate different formats of procurement documentation K4. evaluate methods of identifying and shortlisting suppliers K5. evaluate methods of conducting a tendering procedure K6. critically evaluate methods of securing internal resources in a matrix organisation K7. evaluate how assurance applies to procurement | Candidate can: P1. plan and initiate procurement P2. identify potential suppliers P3. tender for external supplies P4. negotiate for internal resources and develop service level agreements P5. maintain procurement documentation P6. assure the quality of procurement |

| Manage Resources |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 24. Manage Contracts | The purpose of this competency is to achieve the goals of contract management, i.e. to: - support procurement by negotiating terms and conditions - document contractual agreements - monitor contractual performance - conclude contracts |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on contracts and contractual relationships K2. analyse a procedure for managing contracts K3. Evaluate different formats of contract documentation K4. analyse relevant standard forms of contract K5. evaluate how assurance applies to contract management | Candidate can: P1. plan and initiate contracts P2. negotiate contract terms and conditions P3. adapt standard terms and conditions P4. develop and maintain contract documentation P5. assure the quality of contract management |

| Manage Resources |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 25. Mobilise Resources | The purpose of this competency is to achieve the goals of mobilisation, i.e. to ensure that: - capital assets are operational and accessible - facilities are operational and accessible - delivery team members are competent and capable - all resources are redeployed, returned or disposed of, at the end of the work |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on mobilisation and demobilisation of resources K2. analyse procedures for mobilisation and demobilisation K3. evaluate different formats of the relevant documentation K4. critically evaluate methods of working with other managers in a matrix organisation K5. evaluate methods of coordinating multiple suppliers K6. evaluate relevant employment legislation K7. evaluate mechanisms for disposal of capital assets K8. evaluate how assurance applies to mobilisation and demobilisation | Candidate can: P1. plan and initiate mobilisation P2. mobilise resources at relevant points in the life cycle P3. demobilise resources at relevant points in the life cycle P4. maintain relevant documentation P5. assure the quality of mobilisation and demobilisation |

| Interpersonal Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 26. Communicate (M) | The purpose of this competency is to achieve the goals of communication in the P3 context, i.e. to: - impart relevant information - ensure the information is understood |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on communication K2. critically evaluate different forms of communication K3. evaluate factors that affect the effectiveness of communication and potential barriers to communication K4. evaluate how to tailor a message to its intended audience | Candidate can: P1. determine what needs to be communicated and its context P2. identify the target audience and establish any preferred methods and language P3. identify potential barriers to communication and seek to reduce them P4. deliver communication in an effective and timely way P5. ensure that team members and stakeholders have the opportunity to communicate their views P6. seek feedback on the effectiveness of communication and act accordingly |

| Interpersonal Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 27. Manage Conflict (M) | The purpose of this competency is to achieve the goals of conflict management in the P3 context, i.e. to: - utilise the positive aspects of conflict - resolve organisational and interpersonal conflict - minimise the impact of conflict on objectives |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on conflict management K2. evaluate the use of conflict as a normal element of team development K3. critically analyse typical causes and sources of conflict K4. analyse the relationship between magnitude and frequency of conflict K5. evaluate models for conflict resolution K6. evaluate relevant and available external resources for conflict resolution | Candidate can: P1. identify potential areas of conflict and, if necessary, take action to prevent or mitigate these P2. encourage team members and stakeholders to resolve conflict amongst themselves P3. examine the conflict from all parties’ viewpoints P4. consider how to resolve the situation and seek external help where appropriate P5. negotiate and communicate the agreed solution |

| Interpersonal Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 28. Delegate (M) | The purpose of this competency is to achieve the goals of delegation in the P3 context, i.e. to: - allocate work effectively to individuals teams and suppliers within the project, programme or portfolio - use delegation as a motivation and development tool |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on delegation K2. critically analyse how to select and define work for delegation, and when not to delegate K3. evaluate methods of setting targets and monitoring progress towards them K4. evaluate methods of supporting those to whom work has been delegated K5. analyse the broader impact of delegation on the project and project management team | Candidate can: P1. decide which tasks and responsibilities need to be delegated P2. choose people that are competent and available to do the work P3. describe and explain the targets and scope of the work P4. make sure people understand what needs to be done P5. encourage progress by giving advice, support and training P6. suggest ways to solve any problems that arise P7. monitor delegated work to check that agreed targets are met |

| Interpersonal Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 29. Lead (M) | The purpose of this competency is to achieve the goals of leadership in the P3 context, i.e. to: - provide focus and promote commitment to objectives - inspire team members to successfully achieve the objectives |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on leadership K2. evaluate different styles of leadership and your own natural style K3. evaluate how leadership can adapt with the development of the team K4. evaluate different approaches to motivation K5. analyse the importance of ethical and professional behaviour | Candidate can: P1. clearly communicate a team’s collective and individual objectives P2. involve team members in planning how to achieve objectives P3. adopt a leadership style appropriate to the circumstances P4. seek feedback and adapt behaviours accordingly P5. encourage and motivate the team P6. behave ethically and professionally |

| Interpersonal Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 30. Influence | The purpose of this competency is to achieve the goals of influencing in the P3 context, i.e. to: - develop and maintain a high performing team - persuade stakeholders to support the objectives - persuade stakeholders to support the achievement of the objectives |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on influencing K2. critically evaluate how behaviour influences others K3. evaluate the need to, and importance of, identifying people who will positively influence others K4. critically evaluate methods of identifying obstacles and ways to overcome them K5. critically analyse ways of assessing the success of influencing | Candidate can: P1. identify ways in which you can best meet the needs of others whilst meeting your own objectives P2. maintain effective working relationships P3. secure champions for particular aspects of the work P4. develop and present convincing arguments for the principles underlying the objectives P5. communicate persuasively to gain support for the objectives |

| Interpersonal Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 31. Negotiate | The purpose of this competency is to achieve the goals of negotiation in the P3 context, i.e. to: - find solutions to issues involving two or more parties - develop beneficial relationships between two or more parties |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on negotiation K2. critically evaluate different types of negotiation K3. analyse the importance of planning for negotiation K4. evaluate different bargaining techniques K5. evaluate the role of external parties in areas such as mediation and arbitration K6. evaluate methods of documenting the outcomes of a negotiation | Candidate can: P1. initiate and conduct a negotiation P2. decide on the desired outcome and minimum acceptable position P3. determine a negotiation strategy P4. use bargaining techniques to reach a mutually acceptable conclusion P5. use external parties if appropriate P6. ensure the implementation of the negotiation’s outcomes |

| Interpersonal Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 32. Work Within a Team (M) | The purpose of this competency is to achieve the goals of teamwork in the P3 context, i.e. to: - create a team from a collection of individuals - develop and maintain the performance of the team |  |
|  | Candidate can: K1. critically evaluate the context of the work and its impact on teamwork K2. evaluate the roles that different individuals perform within a team and why this is important K3. evaluate the typical development phases that a team goes through and how a team is affected by the different phases of the P3 life cycle K4. evaluate the impact of working as a virtual team | Candidate can: P1. work with others to maximise your and their contribution to team objectives P2. help the team work through the phases of team development P3. demonstrate commitment to the team’s objectives P4. manage personal objectives, keep promises and highlight issues as soon as possible |

| Process Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 33. Identify a Project or Programme | The purpose of this competency is to achieve the goals of the identification process, i.e. to: - develop an outline of the project or programme and assess whether is it likely to be justifiable - determine what effort and investment is needed to define the work in detail - gain the sponsor’s authorisation for the definition phase |  |
|  | Candidate can: K1. evaluate the typical activities that make up the process K2. critically evaluate the context of the work and its impact on the process K3. evaluate application of the relevant functional procedures at an appropriate level of detail for a project K4. analyse the difference between a project and a programme, and the circumstances in which either form of governance is applied K5. evaluate different formats of a brief and definition plan K6. evaluate how assurance applies to the process | Candidate can: P1. perform initial requirements management P2. identify and review lessons learned and prepare high level delivery plans P3. assess whether the project or programme is justifiable P4. decide whether to govern the work as a project or a programme P5. plan the definition phase P6. prepare and present the brief and definition plan to the sponsor P7. assure the quality of the process |

| Process Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 34. Sponsor a Project or Programme | The purpose of this competency is to achieve the goals of sponsorship through the sponsorship process, i.e. to: - provide ownership of the business case - act as champion for the objectives of the project or programme - make go/no go decisions at relevant points in the life cycle - address matters outside the scope of the manager’s authority - oversee assurance - give ad-hoc support the management team |  |
|  | Candidate can: K1. evaluate the typical activities that make up the process K2. critically evaluate the context of the work and its impact on the process K3. evaluate assurance of effective governance K4. Critically evaluate methods of leading, motivating and influencing team members and stakeholders K5. analyse a life cycle based process for the management of projects and programmes | Candidate can: P1. communicate the objectives of the project or programme P2. oversee the creation of the management team P3. motivate and support the management team P4. influence stakeholders P5. resolve issues outside the manager’s control P6. make informed decisions about whether the work should be continued or closed P7. ensure the work is being managed effectively P8. assure the quality of the process |

| Process Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 35. Define a Project or Programme | The purpose of this competency is to achieve the goals of the definition process, i.e. to: - develop a detailed picture of the project or programme - determine whether the work is justified - describe governance policies that describe how the work will be managed - gain the sponsor’s authorisation for the delivery phase |  |
|  | Candidate can: K1. evaluate the typical activities that make up the process K2. critically evaluate the context of the work and its impact on the process K3. evaluate application of the relevant functions to suit the context of the work K4. evaluate different formats of both governance and delivery plans K5. analyse the need to identify pre-authorisation work and agree it with the sponsor K6. evaluate the approach to mobilise for the first stage or tranche of work K7. evaluate how assurance applies to the process | Candidate can: P1. obtain appropriate resources for detailed scope definition P2. research, describe and document scope P3. plan the governance and delivery of the work P4. maintain communication with the sponsor P5. consolidate, summarise and present information to the sponsor for authorisation P6. perform any pre-authorisation work as necessary and mobilise the project or programme after authorisation P7. assure the quality of the process |

| Process Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 36. Deliver a Project or Programme | The purpose of this competency is to achieve the goals of the delivery process, i.e. to: - delegate responsibility for producing deliverables to the appropriate people - monitor the performance of the work and track against the delivery plans - take action where necessary to keep work in line with plans - escalate issues and replan if necessary - accept work as it is completed - maintain communication with all stakeholders |  |
|  | Candidate can: K1. evaluate the typical activities that make up the process K2. critically evaluate the context of the work and its impact on the process K3. evaluate approaches to creating and delegating work packages K4. evaluate techniques for tracking progress, including consolidation across multiple work packages K5. evaluate approaches to identifying potential issues and resolving or escalating them K6. evaluate approaches to communicating progress K7. evaluate how assurance applies to the process | Candidate can: P1. define, delegate and accept work packages P2. monitor and co-ordinate progress across work packages P3. review and accept completed work P4. predict issues, take corrective action and escalate as required P5. prepare exception plans and submit for authorisation P6. maintain effective communication at all times P7. assure the quality of the process |

| Process Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 37. Develop Products | The purpose of this competency is to achieve the goals of the development process, i.e. to: - transfer responsibility for a package of work - execute the package of work - transfer ownership of the finished products |  |
|  | Candidate can: K1. evaluate the typical activities that make up the process K2. critically evaluate the context of the work and its impact on the process K3. evaluate approaches to receiving, planning, monitoring, reporting progress, and handing over completed products for a work package K4. analyse the technical skills required to perform the work K5. evaluate how assurance applies to the process | Candidate can: P1. understand the work package specifications P2. plan the performance of the work P3. ensure the work is performed to the required standard and report progress P4. hand products over to the originator of the work package P5. assure the quality of the process |

| Process Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 38. Manage Boundaries | The purpose of this competency is to achieve the goals of the boundaries process, i.e. to: - conclude a stage or tranche in a structured way - prepare for the next tranche or stage |  |
|  | Candidate can: K1. evaluate the typical activities that make up the process K2. critically evaluate the context of the work and its impact on the process K3. analyse the need to identify pre-authorisation work and agree it with the sponsor K4. evaluate different formats of documentation used to submit an authorisation request to the sponsor K5. critically evaluate the approach to mobilising and de-mobilising resources K6. evaluate how assurance applies to the process | Candidate can: P1. prepare for the closure of a stage or tranche of work P2. review the previous stage or tranche P3. review governance and plan delivery of the next stage or tranche based on previous performance P4. submit documentation for approval of the next stage or tranche P5. mobilise the next stage or tranche P6. assure the quality of the process |

| Process Competencies |  |  |
| --- | --- | --- |
| Competency | Knowledge and Understanding | Professional Practice |
| 39. Close a Project or Programme | The purpose of this competency is to achieve the goals of the closure process, i.e. to: - close a project or programme that has delivered all its outputs - close a project or programme that is no longer justifiable |  |
|  | Candidate can: K1. evaluate the typical activities that make up the process K2. critically evaluate the context of the work and its impact on the process K3. evaluate the approach to successfully handing over products K4. evaluate the approach to document and hand over follow-on actions, and the importance of doing so K5. evaluate how assurance applies to the process | Candidate can: P1. prepare for the closure of the project or programme P2. hand over products to the appropriate stakeholders P3. review the conduct and performance of the project or programme P4. demobilise the organisation and infrastructure P5. assure the quality of the process |